## Annual Operating Plan
BUILDING THE INTER-AMERICAN BIODIVERSITY INFORMATION NETWORK
ANNUAL WORK PLAN
PERIOD: SECOND YEAR (January 1 - December 31, 2006)
[8 empty] | ene-mar | abr-jun | jul-sep | oct-dec
COMPONENT/ SUBCOMPONENT/ACTIVITY | ESTIMATED OUTPUTS |  | ESTIMATED COSTS | Sources of Funding | [7 empty] | Responsible for Execution | COMMENTS
| DESCRIPTION | UNITS |  | GEF |  | COFINANCING |  | GEF Installments
|  |  |  | Amount | % | Amount | % | Q1 | Q2 | Q3 | Q4
INTEROPERABILITY AND ACCESS TO DATA
2.1.1 - IABIN Catalogue Service
2.1.1.1 Develop IABIN catalogue service |  |  | 270000 | 90000 | 33.33% | 180000 | 66.67% | 22500 | 22500 | 22500 | 22500 | Firm/IABIN Secretariat / IEC / OAS
TOTAL |  |  | 270000 | 90000
4a.1.2 - Specimens and Species Thematic Network
4a.1.2.1 Definition of needs | Information from data providers and users | 2 analyst ($2,300 x 1month =$4,600) and office supplies ($200x1month*2=$400) | 5000 | 5000 | 100% | 0 | 0% | 5000
| Acquisition and maintenance of equipment, infrastructure and software, and other staff costs. | 7 computers ($10,500), backup tapes($1,200) and security equipment ($10,000). | 408900 | 21700 | 5.307% | 387200 | 94.69% | 10500 | 11200
4a.1.2.2 Need analysis and design an integrated portal to access information on species | Draft document on policies for use of information | 1 contract ($5000 x consultancy (3 months)=$5000) | 5000 | 5000 | 100% | 0 | 0% | 5000 |  |  |  |  | Short list: Museo Argentino de Ciencias Naturales
| Draft proposal for the portal designated for Species for functionality of the caption tool and software for data providers and workshop | 1 analyst ($2,300 x 5 months =$11,500) and office supplies ($200x5months=$1000) ¦ 1 workshop ($21,200) | 33700 | 33700 | 100% | 0 | 0% | 5000 | 7500 | 21200
| Draft proposal for the portal designated for Specimens for functionality of the caption tool and software for data providers and workshop | 1 analyst ($2,300 x 5months =$11,500) and office supplies ($200x5months=$1000) ¦ 1 workshop ($17600) | 30100 | 30100 | 100% | 0 | 0% | 5000 | 7500 | 17600
| Prepare an initial analysis document of the tool for capturing data, the data provider software for both networks and the portal and the document that defines the policies on the use of information. | 2 analysts ($2,300 x 4 months x 2 =$18400) and office supplies ($200x 4 months x 2 =$1600) | 20000 | 20000 | 100% | 0 | 0% |  |  | 15000 | 5000
| Analysis and incorporation of recommendations acording to schedule and the selected standards. | 2 analysts ($2,300 x 1 month x 2 =$4,600) and office supplies ($200x 1 month x 2 =$400) | 5000 | 5000 | 100% | 0 | 0% |  |  |  | 5000
| Analysis and design of the system components and design of data bases. | 3 contracts ($5,000 x consultancy=$15,000), 3 analysts ($2,300 x 1 month x 3 =$6,900) and office supplies ($200x 1 months x 4 =$800) | 30000 | 22700 | 75.67% | 7300 | 24.33% |  |  |  | 22700
4a.1.2.3 Project Administration | Preparation of Financial Monitoring Reports, Budget control, Aquisitions management, administrative Follow-up, Activities coordination, network representation in international fora, and support for the Secretariat fund-raising activities. | 1 /2 project coordinator ($5000 x 12 months =$30,000 ) and office supplies ($200x12months=$2,400), 1 administrative assistant ($1,200 x 12 months = $14,400) and office supplies ($200x12 months=$2,400) | 99200 | 49200 | 49.6% | 50000 | 50.4% | 12300 | 12300 | 12300 | 12300
4a.1.2.4 Implementation | System development for data management of the experts directory on species and specimens information. | 1 analyst ($2,300 x 4 months =$9,200) and office supplies ($200x4months=$800) and 1 graphical designer ($2,000 x 1 month x 1/4 = $500) | 10500 | 10500 | 100% | 0 | 0% |  |  | 5000 | 5500
4a.1.2.5 Administration on the configuration and changes | Implement a communication system and users support to allow cooperative work, news, report on advance, current changes and versions of standards, tools and protocols and user-help on installation and use of tools developed. | 1 programmer ($1,800 x 4 months =$7,200) and office supplies ($200x4monthsx1=$800) and 1 graphical designer ($2,000 x 2 months x 1/2 = $2000) | 20000 | 10000 | 50% | 10000 | 50% | 7000 | 3000
4a.1.2.6 Software in operation | Design and install the web site for the central server - 1st version and administrate and maintain the network infrastructure. | 1 programmer ($1,800 x 3 months =$5,400) and office supplies ($200x3monthx1=$600) and 1 graphical designer ($2,000 x 2 month x 1/2 = $2000) and office supplies ($200x2monthsx0,5=$100) and 1 analyst ($2,300 x 1 months x 1/2=$1,150) and office supplies ($200x1monthsx0,5=$100) | 16950 | 9450 | 55.75% | 7500 | 44.25% |  | 6350 | 3100
TOTAL |  |  | 684350 | 222350 | 32.49% | 462000 | 67.51%
4a.1.4 Ecosystems Thematic Network
4a.1.4.1 Develop IABIN catalogue service |  |  | 430000 | 140000 | 32.56% | 290000 | 67.44% | 0 | 46000 | 46000 | 48000 | Julie Chan
TOTAL |  |  | 430000 | 140000 | 32.56% | 290000 | 67.44%
2.1.5 Invasive Species Thematic Network
3154 -- Meeting of the technical working group | 2nd TWG face-to-face meeting | 1 meeting | 25000 | 15000 | 60% | 10000 | 40% | 17000 | 17000 | 17000 | 17000 | USGS/OAS
2151 -- Develop data entry tools and training | I3N Capacity Building | 1 contract | 3000 | 3000 | 100% | 0 | 0% |  |  |  |  | Marco Gaiani | Prepare fact sheets with 10 successful stories
2152 -- Search and and retrieval tools | Update of I3N search tool | USGS staff, cofinancing only | 5000 | 0 | 0% | 5000 | 100% |  |  |  |  | USGS/OAS
| Central website update | 1 contract | 25000 | 10000 | 40% | 15000 | 60%
| Central website translation to Spanish and Portuguese | 2 contracts | 11500 | 5000 | 43.48% | 6500 | 56.52%
2153 -- Value added tools | Tool support, enhancement, and maintenance | 2 contracts | 23000 | 8000 | 34.78% | 15000 | 65.22% |  |  |  |  | OAS/USGS
| Promote development of standards for invasive species | 3 contracts | 210000 | 15000 | 7.143% | 195000 | 92.86%
| Development of documents on I3N structure | USGS staff, cofinancing only | 5000 | 0 | 0% | 5000 | 100%
3425 -- Outreach meetings and events | I3N coordination with other IABIN participants and with external organizations | USGS staff, cofinancing only | 30000 | 0 | 0% | 30000 | 100%
| Promotion and outreach: travel to meetings, development and translation of presentations/posters/materials | 5 presentations/posters given at int'l meetings | 32000 | 12000 | 37.5% | 20000 | 62.5%
| Partnership building (e.g., Coordination with GISIN, GISP, TNC) | USGS staff, cofinancing only | 10000 | 0 | 0% | 10000 | 100%
TOTAL |  |  | 300000 | 68000 | 22.67% | 265000 | 88.33%
4a.1.6 Pollinators Thematic Network
4a.1.6.1 Evaluate the information needs of decision makers and set priorities for the development |  |  | 210000 | 70000 | 33.33% | 140000 | 66.67% | 17500 | 17500 | 17500 | 17500 | CI/IABIN Secretariat / IEC / OAS
TOTAL |  |  | 210000 | 70000 |  | 140000
4a.1.7 Protected Areas Thematic Network
4a.1.7.5 Develop AOP and Work Plan | AOP and Work Plan | 1 contract | 24750 | 0 | 0% | 24750 | 100% | 32500 | 16500 | 66000
4a.1.7.1 Formation of a protected area thematic working group (in consultation with designated IABIN leads) | Protected area thematic working group formed | 2 contracts
4a.1.7.3 Develop a draft website | Website hosted | 1 consultant
4a.1.7.1 Identification of potential protected area data providers | List with complete contact information, | 2 contracts
4a.1.7.1 Identify current Protected Area database formats, existing data types, systems used, etc. in 2 countries in each of the six (6) IABIN sub-regions. | Document on prioritized list of data gaps/needs assessment | 1 contract ($5.500,00 x 4 months) | 22000 | 22000 | 100% | 0 | 0%
4a.1.7.1 Develop an annotated document on a prioritized list of data needs and gasps through consultation with data providers and working group | Document on prioritized list of data gaps/needs assessment | [10 empty] | CI/IABIN Secretariat / IEC / OAS
4a.1.7.2 Analyze existing criteria for PA data quality or develop them as needed to be validated during workshop | List of criteria for PA data quality presented | 1 contract ($5.000,00 x 1 month) | 5000 | 5000 | 100% | 0 | 0%
4a.1.7.2 Analyze existing Protected Area Management Effectiveness Tool and propose the most appropiate one to be use consistently by IABIN | Document with proposed ME tool
4a.1.7.2 Propose a minimum set of reporting fields in consultation with the PATWG | Reporting fields and format for network infrastructure developed | 1 contract ($5.500 x.1 month) | 5500 | 5500 | 100% | 0 | 0%
4a.1.7.3 Develop criteria for selection of PATN Experts to be included in PATN Expert Database | List of criteria for selection of PATN Experts defined | 1 contract | 5500 | 0 | 0% | 5500 | 100%
4a.1.7.3 Develop and populate Protected Areas Experts Database and make it available through the PATN Portal | PA Experts Database available through the PATN Portal
4a.1.7.3 Develop and propose structure for a stand-alone PA biodiversity database in consultation with PATWG | Document with proposed structure | 1 contract ($3,300x 5 months) | 16500 | 16500 | 100% | 0 | 0%
4a.1.7.3 Develop a prototypoe PA biodiversity database | Data digitizing tool
4a.1.7.4 Regional Workshop | Prioritized PA Data Needs and Gaps ¦ Proposed minimum set of PA reporting fields ¦ Proposed PA Management Effectiveness Tool ¦ Structure for stand alone Database ¦ Criteria for selection of PATN Experts Database ¦ Criteria for PA data quality ¦ Provide an intereactive training for the prototype a stand-alone Database | 1 workshop | 61000 | 61000 | 100% | 0 | 0%
4a.1.7.3 Propose and develop the structure for Expert Database in collaboration with other TNs | Structure for Expert Database developed in collaboration with other TNs | 1 contract | 2750 | 0 | 0% | 2750 | 100%
4a.1.7.5 Develop and implement PATN Sustainability Plan | PATN Sustainability Plan implemented | 1 contract | 8250 | 0 | 0% | 8250 | 100%
4a.1.7.3 Develop PA Metadata to be accessed by IABIN Catalog | Access PA Metadata by IABIN Catalog | 1 contract | 8250 | 0 | 0% | 8250 | 100%
4a.1.7.3 Develop technical documents on PATN Portal | Technical documents developed | 1 contract | 5500 | 0 | 0% | 5500 | 100%
4a.1.7.3 Upgrade PATN website so that it will give access to PATN data and will allow users to search other TNs | PATN website upgraded | 2 contracts | 11000 | 0 | 0% | 11000 | 100%
4a.1.7.2 Implement the PA Help Desk and respond to user needs | Help Desk implemented | 1 contract | 8250 | 0 | 0% | 8250 | 100%
4a.1.7.2 Host data for those Data Providers who cannot host their own data | Data hosted | 1 contract | 2750 | 0 | 0% | 2750 | 100%
4a.1.7.1 Coordination and communications | Coordinate with other TN CIs and send a representative to the main events of at least the Species and Ecosystems | 1 contract | 5000 | 5000 | 100% | 0 | 0%
| Communicate relevant information to all identified stakeholders |  | 5500 | 0 | 0% | 5500 | 100%
| Functions as the Protected Areas TN coordinator and secretariat | 3 contracts | 46860 | 0 | 0% | 46860 | 100%
4a.1.7.5 Administration, Monitoring and Sustainability | Present quarterly reports to the IABIN Secretariat and the GS/OAS | 1 contract | 8250 | 0 | 0% | 8250 | 100%
| Present annual operation plan to the IABIN Secretariat and the GS/OAS | 1 contract | 5500 | 0 | 0% | 5500 | 100%
| Monitoring and evaluations reports on matching contributions | 1 contract | 22000 | 0 | 0% | 22000 | 100%
TOTAL |  |  | 280110 | 115000 | 41.06% | 165110 | 58.94%
6.1.8 Thematic Network Coordinator | Provides technical guidance to participants and coordinates informatics technologies required to link network resources | 1 OAS Local staff ($4,000x12months) | 44000 | 44000 | 100% | 0 | 0% | 8000 | 12000 | 12000 | 12000 | Boris Ramirez | Hired as a Local OAS Professional staff on January 17, 2005 through January 16, 2006
DATA CONTENT CREATION
2.2.1 Metadata Content Program
2.2.1 Improve the availability of critical metadata data and metadata | Grants to institutions with high quality data to support institutional efforts to make available through the network | 4 Matching grants | 40000 | 40000 | 100% | 0 | 0% | 12500 | 12500 | 12500 | 12500 | IABIN Secretariat/OAS
| Metadata training workshop in collaboration with TNC in Panama (City of Knowledge) | 1 workshop delivered | 20000 | 10000 | 50% | 10000 | 50%
TOTAL |  |  | 60000 | 50000 | 83.33% | 10000 | 16.67%
2.2.2 Specimens Content Program
Improve the availability of critical specimens data and metadata | Grants to institutions with high quality data to support institutional efforts to make available through the network | 4 Matching grants | 40000 | 40000 | 100% | 0 | 0% | 10000 | 10000 | 10000 | 10000 | IABIN Secretariat/OAS
TOTAL |  |  | 40000 | 40000 | 100% | 0 | 0%
Species Content Program
Improve the availability of critical species data and metadata | Grants to institutions with high quality data to support institutional efforts to make available through the network | 4 Matching grants | 40000 | 40000 | 100% | 0 | 0% | 10000 | 10000 | 10000 | 10000 | IABIN Secretariat/OAS
TOTAL |  |  | 40000 | 40000 | 100% | 0 | 0%
Invasive Species Content Program
Improve the availability of critical invasive data and metadata | Training sessions on the use and of data creation tools | 3 training workshops on informatics tools delivered | 24000 | 24000 | 100% | 0 | 0% | 29375 | 29375 | 29375 | 29375 | USGS/OAS
|  | 1 consultant | 8000 | 8000 | 100% | 0 | 0% |  |  |  |  | Marco Gaiani | Finish toolkit/logo/factsheets
|  | 1 consultant | 10500 | 5500 | 52.38% | 5000 | 47.62% |  |  |  |  | Alberto Yanosky | Finish capacity building plan
| Other Data Content Creation | USGS staff, cofinancing only | 135000 | 0 | 0% | 135000 | 100% |  |  |  |  | USGS/OAS
| Grants to institutions with high quality data to support institutional efforts to make available through the network | 8 content-building grants | 80000 | 80000 | 100% | 0 | 0% |  |  |  |  | USGS/OAS
TOTAL |  |  | 257500 | 117500 | 45.63% | 135000 | 52.43%
Data Content Manager | Increase biodiversity information and data content available through IABIN by developing and nurturing partnerships with data and information providers, other biodiversity network iniatives, and users. | 1 OAS Local staff ($4,000x12months) | 44000 | 44000 | 100% | 0 | 0% | 8000 | 12000 | 12000 | 12000 | Rita Besana
INFORMATION PRODUCTS FOR DECISION-MAKING
Develop and/or adapt value-added tool(s) | Make biodiversity information useful to decision-makers in the public and private sectors | One value added tool available | 125000 | 125000 | 100% | 0 | 0% | 31250 | 31250 | 31250 | 31250
TOTAL |  |  | 125000 | 125000 | 100% | 0 | 0%
SUSTAINABILITY OF IABIN
IABIN Secretariat
Director | Increase awareness of IABIN throughout biodiversity community, raise funds, coordinate implementation of network, and supervise Secretariat Staff | 1 OAS Local staff ($5,500x12months) | 60500 | 60500 | 100% | 0 | 0% | 11000 | 16500 | 16500 | 16500 | Ivan Valdespino
Goods |  |  | 15917 | 5000 | 31.41% | 10917 | 68.59% | 1250 | 1250 | 1250 | 1250 | IABIN Secretariat
Travel | Attend workshops and meetings to promote the network and attract resources for the network's activities | 17 travels to attend meetings | 31823 | 26886 | 84.49% | 4937 | 15.51% | 4725 | 3118 | 9421 | 9622
Office supplies and miscellaneous | Furniture and a telephone switchboard for the Secretariat´s office |  | 20970 | 1700 | 8.107% | 19270 | 91.89% | 425 | 425 | 425 | 425
TOTAL |  |  | 68710 | 94086 | 136.9% | 35124 | 51.12%
Partnerships and Communications
Specialized Consultancies | Develop an architecture on IABIN Portal to integrated the TN websites | 1 programmer | 10000 | 10000 | 100% | 0 | 0% | 25112 | 25113 | 25112 | 25113 | IABIN Secretariat
| Improve the design on IABIN Portal | 1 webpage designer | 10000 | 10000 | 100% | 0 | 0%
| Support activities at the IABIN Secretariat | 1 Secretary for the IABIN Secretariat | 12000 | 4800 | 40% | 7200 | 60%
IEC technical meeting | Monitor and discuss the actions developed and to strengten IABIN activities | 1 meeting | 20000 | 20000 | 100% | 0 | 0%
Communication tools, newsletters, brochures | Support to Focal Points to carry out activities for M&E of IABIN GEF Project |  | 10200 | 10200 | 100% | 0 | 0%
| To inform and promote IABIN to the public | 2,000 IABIN brochures | 2000 | 2000 | 100% | 0 | 0%
Meeting, workshops | Data Providers workshops in Chile, Bolivia, Ecuador, Peru and Central America or Canada | 5 workshops delivered | 8250 | 8250 | 100% | 0 | 0%
| Caribbean Bioinformatics Workshop | 1 workshop delivered | 15000 | 15000 | 100% | 0 | 0%
| Workshop for Species and Specimens data providers at the Botanical Congress | 1 workshop delivered | 200 | 200 | 100% | 0 | 0%
| Data content quality or Sistema de Información Biótica© Versión 4.1 | 1 workshop delivered | 20000 | 20000 | 100% | 0 | 0%
TOTAL |  |  | 107650 | 100450 | 93.31% | 7200 | 6.688%
PROJECT ADMINISTRATION
OAS
Operating Expenses | Audits, procurement costs, recurring costs |  | 57708 | 22975 | 39.81% | 34733 | 60.19% | 3975 | 500 | 500 | 18000 | OAS
Administrative and Monitoring Costs | Financial Monitoring reports |  | 209305 | 35463 | 16.94% | 173842 | 83.06% | 8865.75 | 8865.75 | 8865.75 | 8865.75
Travel |  |  | 14000 | 10000 | 71.43% | 4000 | 28.57% | 2500 | 2500 | 2500 | 2500
TOTAL |  |  | 281013 | 68438 | 24.35% | 212575 | 75.65%
GRAND TOTAL |  |  | 3203333 | 1428824 | 44.6% | 1722009 | 53.76% | 306277.75 | 342746.75 | 424898.75 | 354900.75
Component
Subcomponent
Activity
Outputs of the Species TN
Outputs of the Specimens TN.
Note on C6: Outputs= internal activities of a program (i.e. The products and services delivered) What does the program do to achieve its goal or purpose?
Note on H79: cpena: Cofinancing from TNC
Note on B27: cpena: Consultants perform in more than one outputs Julie Chan $4,000 (1.1 $2,000 ¦ 1.2 $2,000) Coordinator $35,000 (4.1 $35,000) Ecosystem Specialist $7,000 (1.2 4,000 ¦ 1.4 $3,000) Systems Expert $22,000 (2.1 $21,000 ¦2.3 $1,000) Programmer Web $7,000 (1.3 $2,000 ¦ 2.1 $3,000 ¦ 2.2 $2,000)
Note on J7: cpena: For the other outputs that are not Convenios (TN) the installments are made upon request of the requirement, I put down for budget purposes
Note on D92: USGS: 4 are carried over from 2005.
Note on H103: cpena: City of Knowledge
Note on H101: cpena: City of Knowledge
Note on H15: William Ulate Rodríguez: Backup and power-supply equipment($14,000) and software use ($65,400), existing servers and other equipment ($98,000) and facilities use($21,000) and infrastructure maintenance($20,000), Internet and local network connectivity and maintenance($20,000) and other staff salaries($148,800).
Note on H21: cpena: 1 analyst ($2,300 x 1 month x 1 =$2,300) and software licenses ($5,000)
Note on H22: cpena: 1 /2 project coordinator ($5000 x 12 months x 0.5 =$30,000 ) and administrative staff salaries ($20,000)
Note on H24: cpena: 1/5 programmer ($1,800 x 4 months x 1/5 =$3,600) and office supplies ($200x4monthsx0,75=$600) and 1 server ($5000) and software licenses ($800)
Note on H25: cpena: 1 analyst ($2,300 x 6months x 1/2=$6,900) and office supplies ($200x6monthsx0,5=$600)